## Example
Example Workplan
Below is an example of how to use this template workplan. You can add rows to include additional activities for a strategy, or delete rows if you only have one or two activities for a strategy. You can also copy and paste to add more rows for other objectives, strategies, and activities. See the TemplateWorkplan tab for an editable workplan.
Objective: | Launch a behavioral health peer support group for BIPOC students at X High School in 2024-2025 school year.
Strategy: | Identify and train peer support leaders by December 2024. | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | Brainstorm potential peer support leaders. | Project team | Behavioral Health Supervisor | Aug-Oct 2024 | List of potential leaders | ID peer support leaders | Staff knowledgeable about student needs/interests
| Recruit peer support leader(s). | Project team | Behavioral Health Supervisor | Oct-Nov 2024 | Leaders selected | Leaders selected | Staff time to talk to students about interest in participating/leading
| Train peer support leader(s). | Project team | Behavioral Health Supervisor | Nov-February 2024 | Training meeting | Leaders feel prepared for hosting peer support group | Staff time to review peer support model, discuss with peer support leader(s)
Strategy: | Promote opportunity to participate in behavioral health peer support group. | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | Develop promotion materials (flyers, student bulletin board, email notice, et.c) | Project team | Behavioral Health Supervisor | Nov 2024 - Jan 2025 | Materials finalized | Students will be aware of opportunity to participate in group and sign up | Staff time to develop; printing for physical materials
| Present at school staff meeting about peer support group. | Behavioral health supervisor |  | 2025-01-01 | Completed presentation | Staff will be aware of peer support opportunity and recommend it to potential students | Staff time to present & discuss with school staff

## TemplateWorkplan
Generic Workplan Template
Objective: | What you plan to achieve by the end of your project.
Strategy: | What is your plan and tools to complete this project | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | How will you achieve your objective
Strategy: | What is your plan and tools to complete this project | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | How will you achieve your objective
Strategy: | What is your plan and tools to complete this project | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | How will you achieve your objective
Objective: | What you plan to achieve by the end of your project.
Strategy: | What is your plan and tools to complete this project | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | How will you achieve your objective
Strategy: | What is your plan and tools to complete this project | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | How will you achieve your objective
Strategy: | What is your plan and tools to complete this project | Staff names | Staff role/responsibility | Activity timeline | Milestones | Desired Outcomes | Resources Required
Activities: | How will you achieve your objective