## Planning Workplan
SBHC Planning Grant - Project Workplan
Please use this workplan template to describe your planning project's activities and deliverables. This template includes required grant activities. Please update the workplan to propose any changes to the required grant activities, deliverables, or due dates; add unique project activities; and assign staff or staff roles to each activity. You can add rows to include additional activities for an objective, or delete rows if you have no additional activities for an objective. You can also copy and paste to add more rows for other objectives and activities.
Objective 1: Participate in trainings, technical assistance, and monthly contract meetings.
Task/Activity | Deliverable | Staff Responsible | Due Date
Attend monthly contract meetings, starting by October 31, 2024, with DOH to discuss project progress and support needs. | Meeting attendance |  | Monthly, starting by 10/31/24
Participate in at least one key training, support, or technical assistance activity per quarter. | Quarterly report of trainings and TA meetings attended |  | Quarterly: 1/15, 4/15, 7/15
[Add any other activities here. Add rows as needed.]
Objective 2: Conduct a community needs assessment.
Task/Activity | Deliverable | Staff Responsible | Due Date
Create a plan and timeline for conducting a community needs assessment. | Community needs assessment plan |  | 2024-10-31
Identify data sources and/or data collection methods to be used in your community needs assessment. | List of data sources and/or data collection methods |  | 2024-12-31
Conduct a community needs assessment. | Quarterly report on progress |  | Quarterly: 1/15, 4/15, 7/15
Summarize community needs assessment findings, including how SBHC would address identified needs. | Community needs assessment report |  | 2025-06-30
[Add any other activities here. Add rows as needed.]
Objective 3: Engage the community, including youth, families, the school/school district, potential SBHC healthcare sponsors, and other relevant organizations or groups in discussions about the SBHC.
Task/Activity | Deliverable | Staff Responsible | Due Date
Develop a community engagement plan, including relationship-building activities with the school and healthcare sponsor, plans for creating an advisory group, and plans for engaging with youth. | Community engagement plan |  | 2024-10-31
Implement community engagement plan. | Quarterly report on progress |  | Quarterly: 1/15, 4/15, 7/15
[Add any other activities here. Add rows as needed.]
Objective 4: Develop a business plan or proposal for a new SBHC.
Task/Activity | Deliverable | Staff Responsible | Due Date
Create an outline for a business plan, proposal, or other planning document for a new SBHC. The final plan should include, at minimum: summary of community's need, SBHC staffing and services, SBHC location, any construction or renovation plans, and SBHC budget and fiscal sources. | SBHC plan outline |  | 2024-10-31
Draft the business plan, proposal, or other planning document for a new SBHC. | Draft SBHC plan |  | 12/31/24, 3/31/25
Finalize the business plan, proposal, or other planning document for a new SBHC. | Final SBHC plan |  | 2025-06-30
Formalize partnership between school or school district and SBHC healthcare sponsor. | Copy of [Memorandum of Understanding, lease agreement, contract, or other formal agreement] |  | 2025-06-30
[Add any other activities here. Add rows as needed.]
Objective 5: [Add any additional project objectives here. Add objectives and activities as needed.]
Task/Activity | Deliverable | Staff Responsible | Due Date
[Add any other activities here. Add rows as needed.]